## Overview
PROJECT MANAGEMENT PLAN AND QUARTERLY PROGRESS REPORT
This Excel workbook serves as a Project Management Plan (PMP) and Quarterly Progress Report (QPR) template. As a grant recipient, you will initially populate this report with baseline project information to constitute your PMP. On a quarterly basis, you will update project information in the report to become your QPR. The PMP and QPR are the same document. The PMP/QPR should be submitted via the Energy Efficiency and Renewable Energy Project Management Center Portal (EERE-PMC Portal). Please see your Assistance Agreement for more information regarding this process. Each State/Indian Tribe (i.e., recipient) is responsible for ensuring that all necessary project information is populated within this document, and that the information denoted is accurate. Contact your DOE Federal Project Officer (FPO) if you have questions while preparing this report. The DOE FPO (also called the Program Manager) is identified in Block 15 of the Assistance Agreement form of your grant. For detailed instructions on completing this workbook, please reference the accompanying 'PMP-QPR Instructions' document.
January
February
March
April
May
June
July
August
September
October
November
December

## Recipient
Project Management Plan and Quarterly Progress Report
Select Submission Month: |  | Enter Submission Day: |  | Enter Submission Year:
Recipient
DOE Grant Agreement Number
DOE Federal Project Officer
Technical Project Manager Name
Technical Project Manager Email
Technical Project Manager Phone Number
Business POC Name
Business POC Email
Business POC Phone Number
Recipient State/Territory |  | State or Territory.
Major Accomplishments During Reporting Period
Planned Work for Next Reporting Period
Items of Note
Quarterly Spend Plan required only if Year 1 + Year 2 Federal allocation amount is greater than $500,000:
QUARTERLY SPEND PLAN
Quarter | Federal Share |  | Non-Federal Share
| Planned | Actual | Planned | Actual
Q0 (Current Reporting Period) | 0 | 0
Q+1 | 0
Q+2 | 0
Administrative & Technical Assistance (TA) Costs
|  |  | Federal Share | Non-Federal Share | Total
Total Federal Grant Amount
Total Admin & TA Costs To Date |  |  | 0 |  | 0
Percentage of Total Federal Grant Amount Used for Admin & TA (May not exceed 5%) |  |  | 0%
BASELINE BUDGET AND INCURRED COST
Budget Category |  | Total Project Budget |  | Prior Cumulative Incurred Cost |  | Incurred Cost During Reporting Period |  | Total Cumulative Incurred Cost
|  | Federal | Non-Federal | Federal | Non-Federal | Federal | Non-Federal | Federal | Non-Federal
Administrative & Technical Assistance (TA) Costs Only:
Personnel | [7 empty] | 0 | 0
Fringe Benefits | [7 empty] | 0 | 0
Travel | [7 empty] | 0 | 0
Equipment | [7 empty] | 0 | 0
Supplies | [7 empty] | 0 | 0
Other | [7 empty] | 0 | 0
Contractual (Admin & TA) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Contractual (Projects) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects (TBD) | [7 empty] | 0 | 0
Project 2 | [7 empty] | 0 | 0
*Insert additional rows for projects as needed. | [7 empty] | 0 | 0
Name (list all other contracts $25,000 or more) | [7 empty] | 0 | 0
*Insert additional rows for contracts $25,000 or more. | [7 empty] | 0 | 0
Sum of individual contracts under $25,000 | [7 empty] | 0 | 0
Sub-Total Direct Charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Charges | [8 empty] | 0
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Percentage (%) of customers within jurisdiction served by utilities that sell not more than 4,000,000 MWh of electricity per year.
Amount ($) of subaward funds that have been made available to Section 40101(d)(6) defined small utilities.
Amount ($) of subaward funds that have been awarded to Section 40101(d)(6) defined small utilities.
Percentage (%) of total Resilience Project subaward funds that have been awarded Section 40101(d)(6) defined small utilities. | [7 empty] | 0%
MILESTONE TABLE
Milestone | Milestone Title |  |  |  |  | Completion Date |  | Status | Items of Note
[6 empty] | Planned | Actual
RM1.1 | Project 1 [Insert Project Name Here] Identified | [6 empty] | Select status.
RM1.2 | Project 1 [Insert Project Name Here] DOE Notification | [6 empty] | Select Status
RM1.3 | Project 1 [Insert Project Name Here] Initiated | [6 empty] | Select status.
RM2.1 | Project 2 [Insert Project Name Here] Identified | [6 empty] | Select status.
RM2.2 | Project 2 [Insert Project Name Here] DOE Notification | [6 empty] | Select status.
RM2.3 | Project 2 [Insert Project Name Here] Initiated | [6 empty] | Select status.
| *Add additional rows as needed | [6 empty] | Select status.
Only For Technical or Admin Support Contracts with a Total Value of $25,000 or More:
TECHNICAL OR ADMINISTRATIVE SUPPORT CONTRACTS
Contractor Name |  | Start Date | End Date | Purpose |  |  |  |  | Total Contract Value
0
*Add additional rows as needed.
RISK MANAGEMENT LOG
Risk |  |  |  | Likelihood (High, Medium, Low) | Impact (High, Medium, Low) | Potential Impact |  | Mitigation Strategy
|  |  |  | Select one. | Select one.
|  |  |  | Select one. | Select one.
|  |  |  | Select one. | Select one.
*Add additional rows as needed |  |  |  | Select one. | Select one.

## Project 1
Project Management Plan and Quarterly Progress Report
Select this Reporting Period's Federal Fiscal Year Here.
Select Reporting Period's Quarter Here.
DOE Grant Agreement Number
Project ID Number
Project Organization or Subawardee
Project Title
Project Performance Period Start Date (mm/dd/yyyy)
Project Performance Period End Date (mm/dd/yyyy)
Project State/Territory
Project Location 5-Digit Zip Code(s) Use commas to separate entries.
Benefitted Community 5-Digit Zip Code(s) Use commas to separate entries.
Subaward Business POC
Subaward Business Address
Subaward Congressional District(s) Reference: https://www.census.gov/mycd/
Subaward Project Manager/Lead (name)
Is this work being performed by a subawardee that qualifies as a Section 40101(d)(6) defined small utility? |  | Select one.
Number of customers (i.e., meters) served by the entity performing the project:
Number of customers (i.e., meters) that are expected to see benefits from the project:
BIL 40101(d) Category of Subawardee: Review the list and delete all categories that do not match your role as a Subawardee in this project. Do not add any other categories or text unless approved by DOE. |  | * Distribution Provider * Electric Grid Operator * Electricity Generator * Electricity Storage Operator * Fuel Supplier * Transmission Owner/Operator * Other (as approved by DOE)
BIL 40101(d) Category of Work: Review the list and delete all categories of work that are not related to the work that you will do during this project. Do not add any other categories or text unless approved by DOE. |  | * Adaptive Protection Technologies * Advanced Modeling Technologies * Battery-Storage Components: Use of DERs for Enhancing System Adaptive capacity During Disruptive Events * Battery-Storage Components: Use or Construction of DERs for Enhancing System Adaptive capacity During Disruptive Events * Fire-resistant Technologies and Fire Prevention Systems * Hardening of Power Lines, Facilities, Substations, or Other Systems * Microgrids: Use of existing DERs for Enhancing System Adaptive Capacity During Disruptive Events * Monitoring and Control Technologies * Reconductoring of Power Lines with Low-Sag, Advanced Conductors * Relocation of Power Lines * Replacement of Old Overhead Conductors & Underground Cables * Undergrounding of Electrical Equipment * Utility Pole Management * Vegetation and Fuel-Load Management * Weatherization Technologies and Equipment * Other (as approved by DOE and noted in Project Description below)
Project Description
Project Benefit Type(s) Review the list and delete all categories of benefits that are not related to the benefits that will be provided by this project. Do not add any other categories or text unless approved by DOE. |  | * Preventing Initial Outages * Preventing Cascading Outages * Providing Contingency Power * Reducing Restoration Time * Adding System Redundancy * Adding System Reconfiguration Capability * Supporting Islanded Operations * Replacing Aging Infrastructure * Other (noted in Benefit Description)
Project Benefit Description
Major Accomplishments During Reporting Period
Planned Work for Next Reporting Period
Items of Note
BASELINE BUDGET AND INCURRED COST
Budget Category |  | Total Approved Project Budget |  | Prior Cumulative Incurred Cost |  | Incurred Cost During Reporting Period |  | Total Cumulative Incurred Cost
|  | Federal | Non-Federal | Federal | Non-Federal | Federal | Non-Federal | Federal | Non-Federal
Personnel | [7 empty] | 0 | 0
Fringe Benefits | [7 empty] | 0 | 0
Travel | [7 empty] | 0 | 0
Equipment | [7 empty] | 0 | 0
Supplies | [7 empty] | 0 | 0
Construction | [7 empty] | 0 | 0
Other | [7 empty] | 0 | 0
Contractual |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Name (list all other contracts $25,000 or more) | [7 empty] | 0 | 0
Name (list all other contracts $25,000 or more) | [7 empty] | 0 | 0
Sum of individual contracts under $25,000 | [7 empty] | 0 | 0
Sub-Total Direct Charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Charges
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILESTONE TABLE
Milestone | Milestone Title |  |  |  |  | Completion Date |  | Status
[6 empty] | Planned | Actual
PM1.1 | Project Start (e.g., Award Contract) | [6 empty] | Select Status
PM1.2 | Planning Complete | [6 empty] | Select status.
PM1.3 | Design Complete | [6 empty] | Select status.
PM1.4 | Regulatory Approval Obtained (including NEPA & Required Permits) | [6 empty] | Select status.
PM1.5 | Equipment / Materials Purchased | [6 empty] | Select status.
PM1.6 | Construction / Installation Started | [6 empty] | Select status.
PM1.7 | Construction / Installation 50% Complete (define milestone marker here) | [6 empty] | Select status.
PM1.8 | Construction / Installation 100% Complete | [6 empty] | Select status.
PM1.9 | Project Complete / Closed-Out | [6 empty] | Select status.
BUILD METRICS (Information about project attributes)
Metric (select from list) |  |  | Type (character lim: 300) |  | Goal Value | Progress
[6 empty] | Value During Reporting Period | Cumulative Value for Project Duration
RISK MANAGEMENT LOG
Risk |  |  |  | Likelihood (High, Medium, Low) | Impact (High, Medium, Low) | Potential Impact |  | Mitigation Strategy
Permitting and regulatory approvals may delay implementation of project. |  |  |  | Select one. | Select one.
Supply chain issues may impact availability of equipment causing project delays. |  |  |  | Select one. | Select one.
Weather or other factors delay impelmentation. |  |  |  | Select one. | Select one.
Unforseen cost overruns. |  |  |  | High | Select one.
*Add additional rows as needed |  |  |  | Select one. | Select one.
|  |  |  | Select one. | Select one.
Provide additional explanation of Risk Impacts and Mitigation Strategies (if needed)

## Build Metrics Table Info
Categories | Table of Possible Build Metrics
Distribution modifications | Miles of new distribution lines
Miles of distribution lines undergrounded
Miles of distribution lines of vegetation clearing
Miles of distribution lines reconductored
Miles of distribution lines with other upgrades (specify in "Type" field what was upgraded)
Number of distribution poles inspected
Number of distribution poles replaced
Number of distribution poles with other upgrades (specify in "Type" field what was upgraded)
Transmission modifications | Miles of new transmission lines (specify capacity (GW-mile) in "Type" field)
Miles of transmission lines undergrounded
Miles of transmission lines of vegetation clearing
Miles of transmission lines reconductored
Miles of transmission lines with other upgrades (specify in "Type" field what was upgraded)
Number of transmission structures inspected
Number of transmission structures replaced
Number of transmission structures with other upgrades (specify in "Type" field what was upgraded)
Substation Modifications | Number of substations relocated
Number of substations with added physical protection
Number of substations with added sensors/monitors
Number of substations with elevated equipment
Number of substations with upgraded equipment
Number of substations with other upgrades (specify in "Type" field what was upgraded)
Number of substations with redundant equipment
Monitoring and control devices | Number of fault location, isolation and service restoration (FLISR) devices installed
Number of other monitoring/metering devices installed
Number of other protection or control devices installed
Batteries | Power Rating of battery system installed (MW) (specify mobile or permanent installation in "Type" field)
Is battery system "off-grid", "behind-the-meter" or part of a "microgrid"? (specify in "Type" field)
Energy rating of battery installed (MWh)
Mobile Units | Power rating of mobile back up generation unit (MW)
Voltage rating of mobile substation (kV)
Voltage rating of mobile transformers (kV)
Hardened Generation | Capacity rating of hardened generation (MW) - photovoltaics
Capacity rating of hardened generation (MW) - wind
Capacity rating of hardened generation (MW) - diesel
Capacity rating of hardened generation (MW) - natural gas
Capacity rating of hardened generation (MW) - coal
Capacity rating of hardened generation (MW) - nuclear
Capacity rating of hardened generation (MW) - hydropower
Average annual electricity produced of hardened generation (MWh) - photovoltaics
Average annual electricity produced of hardened generation (MWh) - wind
Average annual electricity produced of hardened generation (MWh) - diesel
Average annual electricity produced of hardened generation (MWh) - natural gas
Average annual electricity produced of hardened generation (MWh) - coal
Average annual electricity produced of hardened generation (MWh) - nuclear
Average annual electricity produced of hardened generation (MWh) - hydropower
Fuel supply | Percent increased energy storage capacity in reserve fuel - diesel
Percent increased energy storage capacity in reserve fuel - propane
Percent increased energy storage capacity in reserve fuel - gasoline
Restoration equipment | Number of transportation assets purchased to assist with power restoration (specify equipment in "Type" field)
Number of communications assets purchased to assist with power restoration (specify equipment in "Type" field)
Number of other assets purchased to assist with power restoration (specify equipment in "Type" field)
Operating systems | Percentage of system migrated into new software system (specify software system in "Type" field OMS, ADMS, SCADA, inventory management, workforce management, or other)
Inventory | Percentage increase in pole inventory
Percentage increase in transformer inventory
Percentage increase in equipment inventory (specify type of equipment in "Type" field)
Expected lifetime of new equipment (specify equipment in "Type" field)
Other (insert necessary info in "Type" field)